## Gant Chart
Gantt Chart
The project started from 2nd March, the date following is from 2 to 60, and the number 32 is the 1st April. Same to others. | [6 empty] | 1 | [6 empty] | Planned duration | [5 empty] | Actual start time | [5 empty] | Actual（exceed expectation） | [6 empty] | Complete
Activity | Planned start time | Planned project duration | Actual start time | Actual construction time | Members | Status | Date
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
[W2] Group formation | 2 | 1 | 2 | 1 | All | Done
[W2] Create GitLab landing page (Cancelled) | 3 | 7 | 4 | 3 | All | Done
[W2] Create GitHub landing page (Urgent) | 7 | 6 | 7 | 6 | All | Done
[W3] Client requirements confirm | 10 | 1 | 10 | 1 | All | Done
[W3] Audit preparation | 7 | 6 | 7 | 6 | All | Done
[W3] Track satellite research | 4 | 7 | 4 | 7 | All | Done
[W3] Satellite question & Discussion | 8 | 2 | 8 | 3 | All | Done
[W3] System architechture design | 11 | 4 | 11 | 5 | Yuntao, Weihan | Done
[W4] Learning raspberry PI system & Setup | 14 | 5 | 14 | 5 | Nathaniel | Done
[W4] Learning elasticsearch & Setup | 14 | 5 | 15 | 4 | Guopeng, Weihan | Done
[W4] Learning crawler to fetch data | 14 | 5 | 14 | 5 | Ye, Anzee | Done
[w4] Website design | 19 | 4 | 19 | 4 | Yuntao, Nathaniel | Done
[W4] Specific functions discussion with Client | 19 | 1 | 19 | 1 | All | Done
[W4] Next version system design | 20 | 3 | 20 | 3 | Yuntao | Done
[SW] Setup operating system for rasberry PI | 23 | 4 | 23 | 4 | Nathaniel | Done
[SW] Generate ER diagram | 23 | 2 | 23 | 2 | Guopeng, Weihan | Done
[SW] Function for azimuth angle of satellite | 23 | 3 | 23 | 3 | Anzee, Ye | Done
[SW] Function for elevation angle of satellite | 23 | 3 | 23 | 3 | Anzee, Ye | Done
[SW] Continuing web work (User login system) | 23 | 4 | 23 | 4 | Yuntao | Done
[W5] Build elasticsearch and code for interacting | 28 | 4 | 25 | 7 | Guopeng, Weihan | Done
[W5] Setup operating system for rasberry PI | 28 | 4 | 25 | 4 | Nathaniel | Done
[W5] Write crawlers to get website data | 28 | 5 | 25 | 6 | Anzee, Ye | Done
[W5] Design test flow | 29 | 2 | 25 | 4 | Nathaniel | Done
[MB] Webpage (Input Satellite ID to obtain data) | 32 | 5 | 24 | 10 | Yuntao | Done
[MB] Code API to control hardware device | 32 | 5 | 29 | 4 | Anzee, Ye | Doing
[MB] Webpage (Input Satellite Name to obtain data) (New) | 36 | 3 | 31 | 2 | Yuntao | Doing
[W6] Unit test | 45 | 2 |  |  | All | Not started yet
[W6] Integrate database code into master branch | 47 | 2 |  |  | Guopeng, Weihan | Not started yet
[W6] Integrate crawler into master branch | 47 | 2 |  |  | Yuntao, Nathaniel | Not started yet
[W7] Design algorithm for locating satellite | 49 | 4 |  |  | Yuntao, Nathaniel, Franco, Weihan | Not started yet
[W7] Crawler (Get data from Satellite track website) | 49 | 1 |  |  | Anzee, Ye | Not started yet
[W7] Transport data between server rasberry PI | 49 | 6 |  |  | Anzee, Ye | Not started yet
[W7] Crawler Test | 50 | 2 |  |  | All | Not started yet
[W7] Client feedback & supplimentary requirements | 50 | 1 |  |  | All | Not started yet
[W8] Test the hardware in test flow | 56 | 2 |  |  | All | Not started yet
[W8] Data storage (By elasticsearch) | 56 | 1 |  |  | Guopeng, Weihan | Not started yet
[W8] Storage Test | 56 | 1 |  |  | All | Not started yet
[W8] Integrate host-slave data transport codes into system | 57 | 3 |  |  | Anzee, Ye, Guopeng, Weihan | Not started yet
[W8] Final technical testing | 60 | 1 |  |  | Yuntao | Not started yet
[W9] System Integration | 61 | 1 |  |  | All | Not started yet
[W9] System Test | 62 | 1 |  |  | All | Not started yet
[W9] Performance Test | 62 | 1 |  |  | All | Not started yet
[W9] Fix bugs | 62 | 2 |  |  | All | Not started yet
[W9] Design the optimization process | 63 | 5 |  |  | Yuntao | Not started yet
[W9] Project complete